## Project Planner
Project Management Tool
Project Planner
Fill In Project To-Dos, People Responsible, Challenges, Dates and Duration in the Unshaded Cells.
WARNING: Do Not Change Shaded Cells
Project Start Date: | 2017-01-01
Project End Date: | 2017-05-22
Phase | Key To-Dos | People/Person Responsible | Anticipated Challeges | Est Start Date | Duration (Days) | Effort (Hours) | Est End Date
Discovery | Stakeholder Focus Group Review of Old System Research Capabilities of Vendor Offerings | Planning Team Stakeholders, as needed | Prioritizing feature requests from stakeholders | 2017-01-01 | 20 | 160 | 2017-01-21
Requirements Definition | Prepare: - Roles and Use Cases - System Functions - Data Entities - Data Dictionary - List of capacity, security and other Considerations - Rubric for evaluating RFPS - Final RFP | Planning Team | None | 2017-01-22 | 22 | 160 | 2017-02-13
Evaluate/Develop Solutions | Receive, Review and Evaluate Propsosals Obtain feedback from IT Discuss preferred solutions Review with State Director | Planning Team State Director IT Resource Staff | None | 2017-03-01 | 21 | 120 | 2017-03-22
Quality Assurance | Prepare testing protocol Recruit Alpha and Beta Testers Conduct performance and usability tests Address issues with vendor and/or staff | QA Team Alpha and Beta Testers Vendor IT Resource Staff, if needed | Minor performance/usability issues | 2017-04-01 | 31 | 320 | 2017-05-02
Pre-Launch | Data Conversion Configuration on Hosted Platform Prepare Training Materials Conduct Training | Data System Administrator State Staff (Resource) Vendor State Training Staff Program Staff to be Trained | None anticipated | 2017-05-01 | 21 | 500 | 2017-05-22
Post-Rollout Support | Provide Helpdesk style support via phone for critical issues, and email for questions | State Training Staff | None anticipated | 2017-06-01 | Ongoing | 6 hrs/week | ongoing
Formulas:
Est End Date = [Est Start Date]+[Duration (Days)]

## Sample Rubric
Proposed Solution Evaluation Rubric
| Provider | Data Systems 'R Us | Score | 100%
Requirements |  |  |  | Points Awarded |  | Total Points | Percent of Total
Points: 1=Not Adequate, 2=Mostly Adequate, 3=Completely Adequate
Completeness |  |  |  | 9 | 0 | 9 | 18.75%
| Does system offer all required functions and features? |  |  | 3 |  | 3 | 6.25%
| Does system generate all required NRS/WIOA tables? |  |  | 3 |  | 3 | 6.25%
| Does it offer additional nice-to-have features? |  |  | 3 |  | 3 | 6.25%
Reliability |  |  |  | 12 | 0 | 12 | 25%
| Does system operate consistently and reliably, even under load? |  |  | 3 |  | 3 | 6.25%
| Does system provide sufficiently fast response time, even under load? |  |  | 3 |  | 3 | 6.25%
| Does system appropriately enforce agency's business rules? |  |  | 3 |  | 3 | 6.25%
| Does system provide sufficient data validation checks and alerts? |  |  | 3 |  | 3 | 6.25%
Compatibility |  |  |  | 9 | 0 | 9 | 18.75%
| Will system function within agency's prescribed operating environment? Operating systems? Databases? |  |  | 3 |  | 3 | 6.25%
| Does system meet agency's security/privacy requirements? |  |  | 3 |  | 3 | 6.25%
| Is system capable of receiving and sharing interagency data, as needed for data matching and other needs? |  |  | 3 |  | 3 | 6.25%
Vendor Considerations |  |  |  | 15 | 0 | 15 | 31.25%
| Is agency ownership of data assured? Can data be easily exported for use in another system? |  |  | 3 |  | 3 | 6.25%
| Is continuity of service ensured, should vendor cease operations? |  |  | 3 |  | 3 | 6.25%
| Does vendor take appropriate steps to secure state and participant data? |  |  | 3 |  | 3 | 6.25%
| Can changes in the system be made to address changes in state policies/procedures, if necessary? |  |  | 3 |  | 3 | 6.25%
| Does vendor appear to be responsive and helpful? |  |  | 3 |  | 3 | 6.25%
Cost |  |  |  | 3 | 3 | 3 | 6.25%
| Do system costs—including development, updates, and training costs—meet state requirements? |  |  | 3 |  | 3 | 6.25%

## Project Planner Template (hidden)
Project Management Tool
Project Planner
Fill In Project To-Dos, People Responsible, Challenges, Dates and Duration in the Unshaded Cells.
WARNING: Do Not Change Shaded Cells
Project Start Date: | 2017-01-01
Project End Date: | #VALUE!
Phase | Key To-Dos | People/Person Responsible | Anticiapted Challeges | Est Start Date | Duration (Days) | Effort (Hours) | Est End Date
Discovery | Stakeholder Focus Group Review of Old System Research Capabilities of Vendor Offerings | Planning Team Stakeholders, as needed | Prioritizing feature requests from stakeholders | 2017-01-01 | 20 | 160 | 2017-01-21
Requirements Definition | Prepare: - Roles and Use Cases - System Functions - Data Entities - Data Dictionary - List of capacity, security and other Considerations - Rubric for evaluating RFPS - Final RFP | Planning Team | None | 2017-01-22 | 22 | 160 | 2017-02-13
Evaluate/Develop Solutions | Receive, Review and Evaluate Propsosals Obtain feedback from IT Discuss preferred solutions Review with State Director | Planning Team State Director IT Resource Staff | None | 2017-03-01 | 21 | 120 | 2017-03-22
Quality Assurance | Prepare testing protocol Recruit Alpha and Beta Testers Conduct performance and usability tests Address issues with vendor and/or staff | QA Team Alpha and Beta Testers Vendor IT Resource Staff, if needed | Minor performance/usability issues | 2017-04-01 | 31 | 320 | 2017-05-02
Pre-Launch | Data Conversion Configuration on Hosted Platform Prepare Training Materials Conduct Training | Data System Administrator State Staff (Resource) Vendor State Training Staff Program Staff to be Trained | None anticipated | 2017-05-01 | 21 | 500 | 2017-05-22
Post-Rollout Support | Provide Helpdesk style support via phone for critical issues, and email for questions | State Training Staff | None anticipated | 2017-06-01 | Ongoing | 6 hrs/week | ongoing
Formulas:
Est End Date = [Est Start Date]+[Duration (Days)]